## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2255-swen-261-03-codemonkeys
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page.
Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page.
Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute.
Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description.
Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket.
As a helper I want to add a need to my funding basket. | Given a basket and needs when I move a need then I expect the need to appear in the basket.
Given a basket and needs when I move a need then I expect the need to persist in the basket.
As a Helper I want to remove a need from my funding basket | Given a basket and needs exist when I remove a need then I expect the need to be removed from the basket.
Given I want to remove a need then I expect a button to remove the need from the basket AND data to persist after change.
As a Helper I want to view my funding basket so I know what I am funding | Given a basket exists when I navigate to my basket then I expect to see the contents of the basket.
Given a basket has multiple items when I want to see more items then I expect to be able to scroll to change my view of needs.
As a U-fund-Manager I want to add a new need so we can request support. | Given I am logged in as the admin role, when I click the add need button, then I expect to be able to add a new need to the cupboard.
Given that a new need is added to the cupboard, when a user looks at the cupboard, then they should be able to select the new need.
Given I add a new need with correct information, when I view the cupboard, then I expect to see the changes reflected AND persist after logout/login
As a U-fund-Manager I want to edit a need so its imformation is correct | Given I am logged in as the admin role, when I click the edit need button for a need in the cupboard, then I expect that I can edit the need and the change is saved in the cupboard.
Given a need in the cupboard has been updated, when a user looks in the cupboard, then they should see the updated version of the need and be able to select it.
Given I edit a need with correct information, when I view the cupboard, then I expect to see the changes reflected AND persist after logout/login
As a U-fund-Manager I want to remove a need so that outdated needs are no longer available. | Given a need exists when I delete a need then I expect the need to be removed from the cupboard database.
Given a need exists when I delete a need then I expect the UI to be updated and the need disappears from view.
Given I delete a need when I logout/login then I expect the need to still be gone AND the UI to reflect this permanent change.
Given a need in the cupboard has been updated, when a user looks in the cupboard, then they should see the updated version of the need and be able to select it.
As a U-fund-Manager I want to view all needs so that I can manage them. | Given needs exist in the data when I navigate to home page then I expect to see all needs in UI.
Given previous changes in needs data when I navigate to home page then I expect to see all previous changes reflected in UI.
Given a cupboard has multiple items when I want to see more items then I expect to be able to scroll to change my view of needs.
As an Admin, I want to login and logout, so that I can manage the page. | Given a user is on the login page and uses the admin user name for login, when they press the login button, then they should be logged in as an admin.
Given a user is logged in as admin, when they try to use admin commands, then they should have access to those commands and be able to manage the Ufund campaign.
Given a user is logged in, when they press the logout button, then they should be fully logged out and redirected to the home page, AND any changes made should persist when logging back in.
As a User, I want to login and logout, so that I can help fund needs. | Given a user is on the login page and uses any helper user name for login, when they press the login button, then they should be logged in as a helper.
Given a user is logged in as a helper, when they want to perform any helper-enabled action, then they should have permissions to.
Given a helper is logged in, when they press the logout button, then they should be fully logged out and redirected to the home page, AND any changes made should persist when logging back in.
As the system I want to save helper funding baskets so that helpers see the same basket after logging back in. | GIVEN funding basket containing needs WHEN the user logs out and then logs back in I EXPECT the funding basket contains the same needs that were present before.
As a Helper, I want to checkout so I can fund all selected needs in one click | Given I am logged in as helper and funding basket is not empty, when proceed to checkout then I expect the system to remove the needs from cupboard and funding basket.
Given I am logged in as helper and funding basket is not empty, when I click "checkout" I expect to see a message pop-up including a status and "reciept" of what was purchased.
Given I have previsously checked out, when I logout/login, then I expect to see my "checked out" funding basket is now empty and cupboard changes persist.